## Planning Steps Overview
Washington State Dual Language Program Guide: |  | For Developing and Implementing Dual Language Programs
Step 1: Build Knowledge and Advocacy
a. Develop initial understanding of dual language for district and school leaders, teachers, staff, and families.
b. Recruit a diverse advisory group and secure long-term commitment and involvement at all levels of the organization.
c. Conduct a needs assessment to collect data about students to be served, district resources, and community interests.
Step 2: Develop a Program Mission, Vision, and Goals
a. Collaboratively write clear vision and mission statements with guiding principles based on dual language literacy, research, and policy.
b. Define the three goals of dual language at the local level.
Step 3: Design or Adopt a DL Program Model
a. Determine the dual language program model (90/10, 80/20, 50/50) that best fits student and community needs with consensus among all stakeholders.
b. Develop a consistent, research-based language allocation plan.
c. Design P–12 pathways for long-term program sustainability.
Step 4: Develop Enrollment and Family Outreach Plans
a. Determine clear enrollment policies that allow for equitable access for multilingual English learners who speak the program language.
b. Create outreach plans to inform families about the dual language program, explain enrollment policies and procedures, and ensure ongoing family engagement in the program.
Step 5: Align Curriculum and Resources
a. Review district curriculum and identify high-quality curricular resources in both languages aligned to the language allocation plan.
b. Develop a consistent, research-based language allocation plan.
Step 6: Establish a Staffing and Professional Learning Plan
a. Develop plans for recruiting, hiring, and retaining multilingual teachers and staff members.
b. Design a long-term professional learning plan for teachers, paraeducators, district and school administrators, and board members that ensures deep understanding of best practices for dual language implementation.
c. Align district resources to develop a sustainable plan for ongoing professional development and support.
Step 7: Develop a Plan for Assessment and Program Evaluation
a. Determine how students will be assessed in both program languages in content, language, and literacy to monitor student progress and inform instruction.
b. Develop a clear process for annual evaluation of the dual language program to develop continuous improvement plans at the school and district level.

## Step One
Step 1: Build Knowledge and Advocacy – Washington States Dual Language Program Guide - Pages 6-9
Step 1a. Develop an initial understanding of dual language for district and school leaders, teachers, staff, and families.
Action Steps |  | Complete by | Notes | Next Steps
Determine key advocates
Build an understanding of research & benefits of DL
Register and attend conferences, workshops, and PD opportunities
Step 1b. Recruit a diverse stakeholder group and secure long-term commitment and involvement at all levels.
Action Steps |  | Complete by | Notes | Next Steps
Recruit members for the DL advisory group
Set meeting dates for the DL advisory group
Determine members of the DL workgroup
Identify DL Champions
Step 1c. Conduct a needs assessment to collect data about students to be served, district resources, and community interests
Action Steps |  | Complete by | Notes | Next Steps
Examine demographic trends
Examine disaggregated academic data of current, exited, and never qualified ML students.
Examine qualitative data related to the strengths and challenges of identified student groups
Identify district resources such as staffing, curriculum, and funding for DL implementation
Connect with and foster community partnerships through surveys, community meetings, and focus groups

## Step Two
Step 2: Develop a Program Mission, Vision, and Goals - Washington States Dual Language Program Guide - Pages 10-12
Step 2a. Collaboratively write clear vision and mission statements with a set of guiding principles based on dual language literacy, research, and policy.
Action Steps |  | Complete by | Notes | Next Steps
Determine who the DL program will serve
Determine goals and expected outcome for students
Determine the long-term benefits of the program for the entire community
Determine the key steps for achieving the vision
Determine who will be involved in achieving the vision.
Determine how the program will focus on key tenets of the vision and goals
Step 2b. Define the three goals of dual language at the local level.
Action Steps |  | Complete by | Notes | Next Steps
Determine how grade-level academic achievement will be defined and measured
Determine when a student is considered to be fully bilingual and biliterate
Determine ways that sociocultural competence will be demonstrated and measured
Determine how the vision, mission, and goals will be communicated to stakeholders
Determine who the vision, mission, and goals should be communicated to
Determine which platforms will be used to communicate the program vision, mission, and goals
Determine how often the vision, mission and goals will be revisited as the program continues

## Step Three
Step 3: Design or Adopt a Dual Language Program Model – Washington States Dual Language Program Guide - Pages 13-19
Step 3a. Determine the dual language program model (90/10, 80/20, 50/50) that best fits student and community needs with consensus among all decisionmakers.
Action Steps |  |  | Complete by | Notes | Next Steps
Determine program type (two-way DL, one-way DL, or world language immersion)
Reasearch pros and cons of 90/10, 80/20 and 50/50 models
Determine program model (90/10, 80/20 or 50/50)
Step 3b. Develop a consistent, research-based language allocation plan.
Action Steps |  |  | Complete by | Notes | Next Steps
Determine how literacy in both langauges will be developed across all grades.
Identify grades and courses where students would benefit from particular content areas would benefit from being taught in each partner langauge and how they align with the needs of newcomer students
Determine how designated and integrated ELD will be offered to eligible students enrolled in the DL program.
Design a daily schedule that alligns to the chosen program model and langauge allocation plan.
Step 3c. Design P–12 pathways for long-term program sustainability.
Step 3c. Design P–12 pathways for long-term program sustainability.
Action Steps |  |  | Complete by | Notes | Next Steps
Identify enrollment trends within K-12 feeder patterns, including eligibility for TBIP, community langauge use, Title IA status and LAP eligible student population.
Identify or recruit building level leadership and founding teachers.
Determine if one or more elementary schools within a feeder pattern will host the new program.
Determine how current or planned bilingual teacher initiatives can support teacher supply and high school graduation pathway requirements.
Create retooling and additional training pathways for WL and other multilingual educators.
Calendar preperation periods for transitions as the program rolls-up to middle and high school.
Determine when self contained or partner teacher models will be used.
Assess current and plan for new dual credit, CTE pathways, and elective offerings for inclusion in the language allocation plan.
Determine if heritage langauge programs will provide onramps for middle and high school programs.

## Step Four
Step 4: Develop Enrollment and Family Outreach Plans - Pages 20-23
Step 4a. Determine clear enrollment policies that allow for equitable access with priority for multilingual English learners who speak the program language.
Action Steps |  | Complete by | Notes | Next Steps
Determine where students are located who will most benefit from the program
Decide if transportation will needed and/or provided
Decide how families will be able to opt in or out of the program
Determine how equitable access is ensured and how multilingual learners will be prioritized
Decide what grade levels can students enter the program and what will the requirements for entry into the program
Step 4b. Create plans for outreach to inform families about the program, explain enrollment policies and procedures, and provide family choice.
Action Steps |  | Complete by | Notes | Next Steps
Determine means of communication for outreach and recruitment
Determine which barriers currently exits that may effect program enrollment
Identify resources that can be leveraged to address barriers to enrollment and provide support to families
Identify systems and supports needed and who might need to be trained

## Step Five
Step 5: Align Curriculum and Resources - Pages 24-29
Step 5a. Review district curriculum and identify high-quality curricular resources in both languages aligned to the language allocation plan.
Action Steps |  | Complete by | Notes | Next Steps
Identify district office personel responsible for the curriculum adoption and assessment calendars and the status of each content area and langauge testing.
Identify current guarunteed curriculum and any approved supplemental materials materials
Research the availability current materials in the partner language based on the language allocation plan
Review materials in both languages for bias, authenticity, and quality
Determine curricular choices, translation needs, and funding for procuring materials
Utilize curricular materials to map standards and instructional plans across languages
Step 5b. Procure and create instructional resources in both program langauges.
Action Steps |  | Complete by | Notes | Next Steps
Develop a scope and sequence based on content, language arts, and language development standards.
Create a year-long curriculum map to develop themes and coordinate instruction across languages
Develop unit plans to integrate content, language, and literacy and scaffold instruction
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Katie Sperling I am marking suggested additions or edits in yellow-orange.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Katie Sperling would you mind if I fixed your formatting? Reply: Sure. What formatting? But yes anything to make it better. : )

## Step Six
Step 6: Establish a Staffing and Professional Learning Plan - Pages 30-36
Step 6a. Develop plans for recruiting, hiring, and retaining multilingual teachers and staff members.
Action Steps |  | Complete by | Notes | Next Steps
Identify current staff members who are proficient in the program langauge
Decide how language proficiency of teachers will be determined
Determine how many bilingual staff will be needed as the program roles up
Determine how many knowledgeable administrators will be required as the program roles up
Determine if human resources and local unions need to be part of the staffing plan
Idenfity organizations that may help with teacher recruitment efforts
Determine who will be part of the interview team and how the team will assess a candidates' language skills
Create a plan to address issues and challenges related to dual language teacher retention.
Identify potential supports for teachers who need to build language skills to reach the required proficiency levels to instruct in the partner language
Step 6b. Design a long-term professional learning plan for teachers, paraeducators, district and school administrators, and board members that ensures deep understanding of best practices for dual language implementation.
Action Steps |  | Complete by | Notes | Next Steps
Determine who what instructional staff working will need training
Determine how many knowledgeable administrators will be required as the program roles up
Determine if human resources and local unions need to be part of the staffing plan
Idenfity organizations that may help with teacher recruitment efforts
Determine who will be part of the interview team and how the team will assess a candidates' language skills
Create a plan to address issues and challenges related to dual language teacher retention.
Step 6c. Align district resources to develop a sustainable plan for ongoing professional development and support.
Action Steps |  | Complete by | Notes | Next Steps
Determine non-istructional time that can be used for aligning of resources and support for PD and collaboration
Determine what funds are available to support professional learning such as coaching, consultants, conferences or collaboration time
Determine who's skills can be levereged to support the program
Identify structures that exist in the district and/or school for professional learning
Determine how dual language professional learning can be integrated into existing professional learning plans and structures
Identify professional learning cycles to be implemented

## Step Seven
Step 7: Develop a Plan for Assessment and Program Evaluation - Pages 37-46
Step 7a. Determine how students will be assessed in both program languages in content, language, and literacy to monitor student progress and inform instruction.
Action Steps |  | Complete by | Notes | Next Steps
Identify existing content, literacy and language asessments, and determine if they are available in both program languages or in the language of instruction
Determine if assessments are culturally and linguistically relevant and facilitate alternative and inclusive assessment methods
Determine if the identified assessments provide a holistic view of each student
Determine if current assessments provide useful data in one or both languages
Review guidance for content assessment
Review guidance for literacy assessment
Review guidance for language assessment
Determine if additional or alternative assessment need to be added to the assessment plan
Develop an assessment plan that outlines frequency, grade levels, and what will be collected at a classroom, school, or district level
Step 7b. Develop a clear process for annual evaluation of the dual language program to develop continuous improvement plans at the school and district level.
Action Steps |  | Complete by | Notes | Next Steps
Determine what data will be collected and how universal MTSS teams, LAP protocols or Federal Programs comprehensive needs assessments can be leveraged
Assemble a team to review and analyze the data and make recommendations for improvement plans
Review guidance on using the Castaneda framework for program evaluation of ELD services and meaningful access for ML students within the DL program
Identify specific areas to prioritize in program and/or school improvement plans